## Sheet1
Development Plan Table
Phase | Time Frame | Tasks | Deliverables | Completed date
Phase 1: Project Setup | Day 1-2 | 1. Set up project folder structure (frontend & backend). | - Complete file structure in place. | 2024-10-21
|  | 2. Initialize Git repository. | - Git initialized and first commit.
|  | 3. Set up environment variables (.env files). | - Environment variables ready.
Phase 2: Frontend Initialization | Day 3-4 | 1. Set up React project. | - React app initialized. | 2024-10-22
|  | 2. Install dependencies (Material UI, Axios, etc.). | - Dependencies installed.
|  | 3. Implement basic routing for pages. | - Basic routing between Home, Dashboard, and History pages.
Phase 3: Backend Initialization | Day 5-6 | 1. Set up Flask/Django project. | - Backend app initialized. | 2024-10-23
|  | 2. Install necessary dependencies (Flask/Django, Azure SDK, etc.). | - Basic API route (e.g., /upload) created.
|  | 3. Set up basic API routes. | - Dependencies installed.
Phase 4: Frontend - Image Upload UI | Day 7-8 | 1. Implement image upload UI (ImageUpload.js). | - Image upload functionality on the frontend.
|  | 2. Validate image upload input. | - Validation of image files (size, format).
|  | 3. Add progress indicator for uploads. | - Basic progress indicator.
Phase 5: Backend - Image Upload API | Day 9-10 | 1. Implement image upload API (app.py). | - Working image upload API.
|  | 2. Set up Azure Blob Storage integration to store images. | - Images stored in Azure Blob Storage.
|  | 3. Test API with Postman. | - Postman-tested API endpoint for uploads.
Phase 6: Machine Learning Model Integration | Day 11-12 | 1. Integrate Azure Cognitive Services or custom ML model for image description. | - ML model integrated into the backend.
|  | 2. Call ML model from backend. | - API returns a 2-line description of the uploaded image.
3. Return 2-line description.
Phase 7: Frontend - Display Results | Day 13-14 | 1. Implement DescriptionResult.js to display the 2-line description. | - Image description displayed on the frontend.
|  | 2. Connect frontend with the backend API. | - Frontend communicates with the backend via API.
|  | 3. Display image and description. | - Handle API response errors on the frontend.
Phase 8: Database Integration | Day 15-16 | 1. Set up Azure Cosmos DB or SQL Database. | - Database schema set up for image history.
|  | 2. Implement database schema for storing image history. | - Backend stores image, description, and metadata in the database.
|  | 3. Integrate database with backend. | - Successful database connection.
Phase 9: User Authentication (Optional) | Day 17-18 | 1. Set up Azure Active Directory B2C for user authentication. | - User login and signup functionality.
|  | 2. Implement user login, signup pages. | - API endpoints secured.
|  | 3. Secure API endpoints with user sessions. | - Basic user management (e.g., see user-uploaded images).
Phase 10: User Dashboard | Day 19-20 | 1. Implement Dashboard.js for user account management. | - User dashboard showing upload history.
|  | 2. Display uploaded image history. | - Connect dashboard to database.
|  | 3. Allow users to view their previous uploads. | - Basic user session management.
Phase 11: Implement Rate Limiting & Usage Tracking | Day 21-22 | 1. Track user uploads in the database. | - Upload usage tracking.
|  | 2. Implement usage limits (e.g., free tier with a set number of uploads). | - Free tier rate limit implemented.
|  | 3. Notify users when limit is reached. | - User notification when limit is reached.
Phase 12: Payment Integration (Optional) | Day 23-24 | 1. Integrate Stripe for payments. | - Stripe payment gateway integrated.
|  | 2. Create pricing plans and integrate payment gateway. | - Pricing plans available.
|  | 3. Update user status upon successful payment. | - Payment status updates and tracking.
Phase 13: UI/UX Enhancements | Day 25-26 | 1. Implement advanced UI features (e.g., dark mode toggle, improved responsiveness). | - UI/UX improvements.
|  | 2. Add animations and better error handling on the frontend. | - Fully responsive design.
- Smooth user interactions with proper feedback mechanisms.
Phase 14: Testing & Debugging | Day 27-28 | 1. Write unit tests for frontend (Jest) and backend (PyTest). | - Unit tests for API endpoints.
|  | 2. Test API integration and database connections. | - Test coverage for frontend components.
|  | 3. Resolve any UI/UX bugs. | - Bug-free integration between frontend and backend.
Phase 15: CI/CD Pipeline Setup | Day 29-30 | 1. Configure Azure DevOps pipeline for automated deployment. | - Fully automated CI/CD pipeline in Azure DevOps.
|  | 2. Set up automated tests in the pipeline. | - Staging environment for testing.
|  | 3. Deploy to staging and production. | - Production deployment with monitoring and alerting.
Phase 16: Deployment & Monitoring | Day 31-32 | 1. Deploy frontend and backend on Azure (App Services, Static Web Apps). | - Live production deployment.
|  | 2. Set up Azure Monitor for tracking API performance and usage. | - Monitoring for uptime, error rates, and performance metrics.
- Alerts set up for high usage and errors.